## DF Coaching Action Log
DF COACHING - ACTION LOG
NO | ITEMS | DETAILS | OWNER | START DATE | END DATE | STATUS | REMARKS
1 | Login and Logout | Handles the authentication and access limitation of accounts | Dizon | Feb 3 | Feb 4 | Closed | Need to Do: 1. Ensure that the logged-in user is authorized to actions that is available and viewed from his/her screen 2. Limit the user's access on some URLs depending on his/her role
2 | Database Designing | The design responsible for the automatic grouping of employees and for data binding | Dizon | Feb 3 | Feb 5 | Closed | Need to Do: 1. Design a database tables that has a related value to each other in order to implement hierarchy design
3 | Admin Control Panel | Controls the web application credentials and data bindings | Dizon + Rosete | Feb 6 | Feb 7 | Closed | Need to Do: 1. Create design for the view with several menu 2. Bind data and implement basic data processing CRUD (Create, Retrive, Update and Delete)
4 | Score Item Linking | Responsible for dynamic binding of actual values from the excel file to the scorecard | Dizon | Feb 17 | Feb 19 | Closed | Need to Do: 1. Implement dynamic scorecard item by creating tables for each function and category that can be updated in Admin Control Panel 2. Determine the data source of the scorecard item by specifying the target worksheet and cell name
5 | Team Hierarchy | The ability of the web application to manage different teams | Dizon | Feb 20 | Feb 21 | Closed | Need to Do: 1. Connect each team member's role to the scorecard item function 2. Organize the team members of leaders by selecting only the agent with the same leader id specified in the database
6 | Web Application Optimization | The speed and reliability of the web application | Rosete | Feb 10 | Feb 11 | Closed | Need to Do: 1. Redesign pages and optimize the page load speed, element animations and the overall structure of the web application
7 | Database Security | System vulnerabilities when instructing the web application to get or set some data | Dizon | Feb 19 | Feb 20 | Closed | Need to Do: 1. Ensure that the current user is authorize to do some action by revalidating the current user's information in the back-end side rather that the front-end side 2. Recheck every action made by the user inside the framework
8 | Form Action Validation | System vulnerabilities when redirecting to URLs which can only be handled by the framework | Dizon | Feb 19 | Feb 20 | Closed | Need to Do: 1. Ensure that the current user is authorize to do some action by revalidating the current user's information in the back-end side rather that the front-end side 2. Recheck every action made by the user inside the framework
9 | Scorecard Data Integration | Scorecard data binding for the specific resource | Dizon | Feb 10 | Feb 25 | Closed | Need to Do: 1. Display the right scorecard item categories depending on the agent's role 2. Get all the actual data row inside the Excel file that matches the agent's ID and bind it in the web application
10 | Notification System | Realtime notification for form actions | Dizon + Rosete | Feb 21 | Feb 21 | Closed | Need to Do: 1. Display notification box in real-time 2. Implementing server polling system that periodically checks if there is a message for the user
11 | Session History | History table of owned sessions filtered by date range | Dizon + Rosete | Feb 20 | Feb 20 | Closed | Need to Do: 1. Display the right sessions when filtered using date range 2. To be able to review the filtered sessions one by one
12 | Feedback Form | Web application feedback form | Dizon + Rosete | Feb 19 | Feb 19 | Closed | Need to Do: 1. Enable all users to send us some feedback using the feedback form
13 | Dashboard Data Integration | The implementation of methods that filters data based on the current user's needs and displays it in his/her dashboard | Dizon + Rosete | Feb 14 | Feb 18 | Closed | Need to Do: 1. Display the right scorecard current scores and their pending/completed sessions depending on the agent's role 2. Display the stack rank (top three only) together with the overall top resource with his/her every status
14 | Coaching, Triad and Scorecard View | The design of the page when viewing/printing the session | Rosete | Feb 10 | Feb 25 | Closed | Need to Do: 1. Design the view of the session that can adapt to Coaching, Scorecard, Triad, etc.. 2. Design the printable view of the session to mimic the current form.
15 | Process Automation | The flexibility of the web application when handling different type of sessions | Dizon | Feb 25 | Feb 26 | Closed | Need to Do: 1. Study the processes of scorecard, coaching and triad sessions 2. Check for similarities of each processes 3. Create database table design that handles static data (agent information, session type, session date, etc..) and dynamic data (input fields, scorecard details, signees, etc..)
16 | Default Database Backup | Adding default values of credentials, scorecard items and account types to the migration which acts as the database backup of the web application | Rosete | Feb 26 | Feb 26 | Closed | Need to Do: 1. Fill database with the default values whenever the web application migrates to another machine 2. Fill database with all the applicable resources' account, current scorecard items, session types and account types
17 | Top Resource and Stack Ranking for all Dashboards | Add Overall Top Resource and Stack Ranking for all leaders | Dizon + Rosete |  |  | Open | Need to Do: 1. Reintegrate data binding in all types of dashboard to handle stack ranking without errors
18 | Data File Link For Realtime Data Update | A system that allows the actual data to be updated daily | Dizon |  |  | Open | Need to Do: 1. Relocate files of the actual data to be read by the web application 2. Create file links to enable editor of the data to edit the Excel file naturally without uploading it on the web application
19 | Feedback View | The view of the collection of feedbacks coming from feedback form | Rosete |  |  | Open | Need to Do: 1. Create view that will list all of the feedbacks of the users
20 | Table Sorting | The ability of the web application to sort tables in the dashboard | Rosete |  |  | Open | Need to Do: 1. Create script using Javascript that lets the user sort any sortable table present on the web application
21 | Change Password | The ability of the web application to change the user's password without using Admin Control Panel | Dizon + Rosete |  |  | Open | Need to Do: 1. Create form that let the user change his/her password without using Admin Control Panel
22 | New Session Format | Updates for the new format of the coaching forms | Dizon + Rosete |  |  | Open | Need to Do: 1. Reformat the view of all type of sessions using the new format
23 | Multiple Roles and Logistic Executive Role | Adding unique and dynamic roles to the database design | Dizon |  |  | Open | Need to Do: 1. Reintegrate data binding in Logistic Executive role because the worksheet of this role is different from all other agent that uses "RESOURCES" worksheet 2. Add another level of database filtering logic for multiple roles
24 | Debugging | Fixing overall reliability issues and bugs throughout the web application encountered during test run | Dizon + Rosete |  |  | Open | Need to Do: 1. Fix remaining bugs and errors found during the test runs
25 | E-Signatures | The ability of the web application to accept and record digital signatures from pen input device | Dizon + Rosete |  |  | On Hold | Need to Do: 1. Redesign how the database record its signature data Note: Right now, we used checkbox that records only '0' (which is false) and '1' (which is false) that determines whether the agent signed his/her session